CONDENSED COMPANION · V1.0 · SEPT–OCT 2026

# SAP Migration — Field Pocket Reference

The one document to carry into a cutover bridge: the sequence, the checks, the return codes and the decision gates. Full rationale, theory and evidence strategy live in the SAP Migration Training Handbook v1.0 — this card deck does not replace it.

| Field | Value |
| --- | --- |
| Document ID | SAP-MIG-TRN-PR-001 |
| Companion to | SAP-MIG-TRN-HB-001 v1.0 (Training Handbook) |
| Owner | Amit Prajapati — primary trainer |
| Use | Cutover bridge, validation desks, hypercare desk |
| Status | Issued with handbook v1.0 |

THREE RULES THAT OVERRIDE EVERYTHING ELSE ON THESE PAGES

1. Nothing advances past a gate without evidence and a named approval.

2. The source stays available until the required final backup activity succeeds.

3. If R3trans -d is not 0000, SAP does not start.

POCKET REFERENCE · SECTION 1

# 1  Cutover run-card

Four lanes, one direction of travel. Each handover is announced on the bridge and recorded in the change log with a timestamp.

LANE SEQUENCE

| APPLICATION | DBA | BASIS / MIGRATION | FUNCTIONAL + PMO |
| --- | --- | --- | --- |
| 1 Cooldown / ramp-up complete 2 Application + web services stopped 3 Handover to DBA confirmed | 4 Final backup + AWS snapshot 5 Switchover or HANA recovery 6 DBVERIFY, RMAN, DB validation | 7 rsync global directory; clean host/IPAM 8 Profile parameters, kernel permissions, root scripts 9 R3trans -d must return 0000 10 Start SAP; validate SNC/SSO, Gateway, RFC | 11 Business transaction tests, interfaces, printers, evidence |

# the gate before SAP start

su - &lt;sid&gt;adm

R3trans -d        # expect: R3trans finished (0000)

cat trans.log     # first place to look if not 0000

# instance state without the GUI

sapcontrol -nr <nn> -function GetProcessList

sapcontrol -nr <nn> -function GetSystemInstanceList

GO/NO-GO GATE INPUTS

| Go/No-Go input | Must be true to vote Go |
| --- | --- |
| Technical validation | Module 4 + Module 6 checks complete, or formally deferred with owner, impact, date |
| Functional validation | Named business transactions passed by the functional team |
| Evidence | Source and target captured, compared, attached to the change record |
| Rollback readiness | Snapshot / final backup verified; DNS rollback path defined; owner on the bridge |
| Approvals | Basis, application, functional, system owner, PMO — recorded by name |
| Open risks | Every item classified; no unexplained critical |
| Support readiness | Hypercare roster, escalation path, ticket routing live |

ROLLBACK PATH (EXECUTED ON NO-GO OR AN UNSAFE CUTOVER)

▪  Restore the snapshot or recover the source; revert DNS/CNAME to the source.

▪  Restart source database and SAP; re-validate connectivity (R3trans -d).

▪  Announce decision, time and reason on the bridge; record evidence of the attempt.

▪  Confirm with the business what data (if any) was created on the target.

Figure 6. Cutover execution sequence with the Go/No-Go decision and rollback path (from the handbook).

POCKET REFERENCE · SECTION 2

# 2  Validation checklists — field copy

Tick, status, evidence reference. Transfer results into the change record before sign-off; an unexplained N/A is an audit finding.

## 2.1  OS

| ☐ | Check | Status | Evidence / remarks |
| --- | --- | --- | --- |
| ☐ | File systems / mount points | Not Started |  |
| ☐ | CPU | Not Started |  |
| ☐ | RAM | Not Started |  |
| ☐ | Swap | Not Started |  |
| ☐ | OS version | Not Started |  |
| ☐ | Kernel version | Not Started |  |
| ☐ | UID/GID | Not Started |  |
| ☐ | Libraries | Not Started |  |
| ☐ | FTP users | Not Started |  |
| ☐ | OS groups | Not Started |  |
| ☐ | IP addresses | Not Started |  |
| ☐ | Hostnames | Not Started |  |
| ☐ | /etc/hosts | Not Started |  |
| ☐ | /etc/services | Not Started |  |
| ☐ | SAP directories | Not Started |  |
| ☐ | Permissions | Not Started |  |

## 2.2  SAP

| ☐ | Check | Status | Evidence / remarks |
| --- | --- | --- | --- |
| ☐ | SAP services active | Not Started |  |
| ☐ | Auto-start tested (real reboot) | Not Started |  |
| ☐ | SAP processes green | Not Started |  |
| ☐ | Application servers available | Not Started |  |
| ☐ | SM51 | Not Started |  |
| ☐ | SMGW | Not Started |  |
| ☐ | SM59 | Not Started |  |
| ☐ | RFC report | Not Started |  |
| ☐ | SNC | Not Started |  |
| ☐ | STMS | Not Started |  |
| ☐ | Transport directory | Not Started |  |
| ☐ | AL11 | Not Started |  |
| ☐ | Printers | Not Started |  |
| ☐ | Spool | Not Started |  |
| ☐ | SMICM | Not Started |  |
| ☐ | SSL/TLS certificates | Not Started |  |
| ☐ | SAP license | Not Started |  |

## 2.3  Database

| ☐ | Check | Status | Evidence / remarks |
| --- | --- | --- | --- |
| ☐ | DB status | Not Started |  |
| ☐ | DB02 | Not Started |  |
| ☐ | Storage utilization | Not Started |  |
| ☐ | Tablespaces | Not Started |  |
| ☐ | Database growth | Not Started |  |
| ☐ | Latest backup | Not Started |  |
| ☐ | Backup status | Not Started |  |
| ☐ | Redo/archive logs | Not Started |  |
| ☐ | Recovery requirements | Not Started |  |

## 2.4  Performance

| ☐ | Check | Status | Evidence / remarks |
| --- | --- | --- | --- |
| ☐ | ST02 memory | Not Started |  |
| ☐ | Extended memory | Not Started |  |
| ☐ | Heap/private memory | Not Started |  |
| ☐ | Buffer utilization | Not Started |  |
| ☐ | ST03N workload | Not Started |  |
| ☐ | Response time | Not Started |  |
| ☐ | Wait time | Not Started |  |
| ☐ | DB request time | Not Started |  |
| ☐ | CPU time | Not Started |  |
| ☐ | Performance trends | Not Started |  |

## 2.5  Cutover readiness

| ☐ | Check | Status | Evidence / remarks |
| --- | --- | --- | --- |
| ☐ | Application shutdown confirmed | Not Started |  |
| ☐ | DBA handover confirmed | Not Started |  |
| ☐ | Source/target synchronization confirmed | Not Started |  |
| ☐ | Snapshot/backup confirmed | Not Started |  |
| ☐ | DNS/IPAM plan confirmed | Not Started |  |
| ☐ | Evidence captured | Not Started |  |
| ☐ | Technical validation complete | Not Started |  |
| ☐ | Functional validation complete | Not Started |  |
| ☐ | Approvals complete | Not Started |  |
| ☐ | Rollback ready | Not Started |  |
| ☐ | Go/No-Go decision recorded | Not Started |  |

POCKET REFERENCE · SECTION 3

# 3  Transactions, commands and files

What each item proves. A screenshot you cannot interpret is not evidence.

SAP TRANSACTION QUICK REFERENCE

| T-code | Proves | T-code | Proves |
| --- | --- | --- | --- |
| SM51 | All planned instances active and registered | ST02 | EM, heap/private, roll, paging, buffer hit ratio |
| SM59 | RFC destinations exist and connect | ST03/ST03N | Response/DB/CPU/wait time and workload trend |
| SMGW | Gateway status and connections | STAD | The individual slow records behind the aggregates |
| SMICM | ICM HTTP/HTTPS services and ports | RZ10 / RZ11 | Persistent profile change / dynamic runtime change |
| STMS | Domain, systems, routes, transport directory | DB02 | Space, tablespaces, growth, backup status |
| AL11 | SAP directories, content, permissions | SPAD / SP01 | Output devices and spool requests |
| STRUST | Certificates: validity, chain, hostname | SLICENSE | License valid for the new hardware key |
| ST22 / SM37 | New dumps / job status after go-live | SM13 / SM12 | Update errors / lock entries |

OS COMMAND QUICK REFERENCE

| Command | Validates |
| --- | --- |
| df -h, mount, lsblk | File systems, mounts, sizes, options |
| lscpu, free -g, swapon -s | CPU, RAM, swap versus build sheet |
| id, getent passwd, getent group | Numeric UID/GID consistency |
| ip a, ip r, hostname -f | IPs, routes, hostname/FQDN |
| getent hosts, nslookup | Resolution — run from the SAP host, not a laptop |
| uname -r, /etc/os-release | Kernel and OS version |
| systemctl status / show | Service state, Result and exit code |
| sapcontrol -nr <nn> -function GetProcessList | Instance process state from the OS |
| R3trans -d | SAP-to-database connectivity (expect 0000) |
| rsync -avn (dry run first) | Global directory synchronisation |

FILES THAT DECIDE WHETHER A CUTOVER WORKS

| File / location | Why it decides the cutover |
| --- | --- |
| /etc/hosts | A stale entry silently overrides DNS and reconnects you to the source |
| /etc/services | sapdp<nn> / sapgw<nn> port definitions |
| /etc/fstab | A missing or misordered mount breaks SAP at boot |
| SAP work/log dirs | dev_w*, dev_disp, dev_ms explain start failures |
| trans.log | First place to look when R3trans -d ≠ 0000 |
| HANA INI files | global.ini, nameserver.ini drive recovery |
| Oracle network files | listener.ora, tnsnames.ora, sqlnet.ora |

POCKET REFERENCE · SECTION 4

# 4  Return codes and first diagnostics

Diagnose before you retry, and never raise a memory parameter before finding what consumes the memory.

CODES YOU WILL ACTUALLY SEE

| Code | Meaning | First actions |
| --- | --- | --- |
| Service 0 | Success | Still confirm instances in SM51 — zero exit ≠ usable SAP |
| Service 127 | Command or shared library not found | ExecStart path, <sid>adm environment, LD_LIBRARY_PATH, migrated libraries |
| Service 255 | Generic start-script/SAP failure | Service journal, dev_disp, dev_ms, dev_w0, DB connect trace |
| R3trans 0000 | SAP ↔ database connectivity OK | Proceed to SAP start |
| R3trans 0012 | Database connect failed | DB open? listener? DB host entry in profile and /etc/hosts? |
| R3trans 0018 | DB authorisation / credentials | User, password, wallet/keystore, credentials handover |

Confirm code meanings against the release and platform in use; treat as a starting point.

MEMORY AND PERFORMANCE SYMPTOM MAP

| Symptom | Investigate first | Owner |
| --- | --- | --- |
| Processes in PRIVATE mode | EM under-sized, long transactions, memory-heavy custom code | Basis + ABAP |
| High paging / swaps | Paging area too small, context held too long | Basis |
| Low buffer hit ratio | Buffer sizing or access patterns bypassing buffers | Basis + DBA |
| High DB time | Access path, statistics, SQL, app-to-DB latency, storage throughput | DBA |
| High CPU time | Custom code, data volume, under-sized instance type | ABAP |
| High wait time | Memory, enqueue, RFC destinations, dispatcher | Basis + interface owner |
| Slow only at peak | Work process saturation, DB contention | Basis + DBA |

THRESHOLD CAUTION

≈1200 ms response time and ≈40% average DB request time are discussion values from the training. Validate against the client baseline and the measured source performance before using them as alerting thresholds.

POCKET REFERENCE · SECTION 5

# 5  Oracle switchover and HANA recovery cards

Planned switchover only — a failover is disaster recovery and is not reversible in the same way.

ORACLE DATA GUARD SWITCHOVER SEQUENCE

| # | Step | Evidence to capture |
| --- | --- | --- |
| 1 | Pre-checks: listener, SQL*Net, DG parameters, SID, Broker, observer, patch alignment | Config outputs |
| 2 | Review log switching and apply lag (zero gap) | v$managed_standby |
| 3 | Compare source and target SCN | v$database.current_scn both sides |
| 4 | Attach evidence to Jira/change; obtain approval | Ticket reference |
| 5 | AWS disk-level snapshot of the target (rollback point) | Snapshot ID + timestamp |
| 6 | Application shutdown confirmed; DBA handover accepted | Bridge log |
| 7 | Close source primary; switchover; open new primary | Command output |
| 8 | Validate new primary; DBVERIFY; RMAN backup; OEM agent | DBVERIFY + RMAN logs |

NAME RESOLUTION AFTER THE ROLE CHANGE

| DNS / IPAM after switchover | Rule |
| --- | --- |
| Virtual hostname | Unchanged — SAP keeps addressing the same name |
| Target IP | Updated in DNS/IPAM |
| CNAME | Repointed to the target environment |
| Resolution | Verified from every consumer with getent hosts + a real R3trans -d |
| Host files | Obsolete entries cleaned — they override DNS |

Source backup  →  Configuration file  →  S3 backend  →  Target configuration  →  Recovery  →  Validation

HANA CONTAINER MODEL IN ONE LINE

SystemDB = central management, monitoring and the backup catalogue; TenantDB = the application workload. Separate logins; both can live on one host; neither is HA — HA is HSR plus cluster/storage design.

CUTOVER RULE

Test backup and recovery before cutover. During cutover: final backup → validate it → only then stop the source. The source stays available until that backup succeeds; it is also your rollback anchor.

POCKET REFERENCE · SECTION 6

# 6  Evidence, hypercare and escalation

Working before migration should work after migration — evidence is what makes that provable at 02:00 on a bridge call.

&lt;SID&gt;_&lt;PHASE&gt;_&lt;CHECK&gt;_&lt;SOURCE|TARGET&gt;_&lt;YYYYMMDD-HHMM&gt;.&lt;ext&gt;

# examples

PRD_PRECUT_SM59_SOURCE_20261002-1015.pdf

PRD_CUTOVER_R3TRANS_TARGET_20261005-0212.log

PRD_CUTOVER_SCN_BOTH_20261005-0140.png

CLASSIFYING A FAILURE IN HYPERCARE

| Before vs after | Classification | Route |
| --- | --- | --- |
| Working → failing | Migration-related | Owning team corrects, retests, re-captures evidence |
| Failing → failing | Pre-existing condition | Document it; route to BAU with baseline evidence |
| Failing → working | Improvement | Record it so it is not rolled back later |
| No baseline | Unclassifiable | Escalate — you cannot prove what you did not record |

HYPERCARE MONITORING SET (15 DAYS)

| Watch daily | Source | Bad trend looks like |
| --- | --- | --- |
| Short dumps | ST22 | New dump types or a rising count |
| Failed jobs | SM37 / Control-M | Jobs cancelled that previously succeeded |
| Interfaces / IDocs | SM59, WE02 | Rising error status, retries not clearing |
| Response time | ST03N | Sustained rise over baseline, same period type |
| Memory | ST02 | PRIVATE mode, rising paging or swaps |
| Database | DB02, alert log | Growth beyond forecast, archive filling, backup failures |
| Updates / locks | SM13, SM12 | Stuck updates, growing lock entries |
| Certificates | STRUST | Expiry approaching, SNC handshake failures |

ESCALATION MODEL

| Severity | Definition | Route |
| --- | --- | --- |
| S1 Critical | Cutover blocked, system down, data at risk, rollback decision | Bridge → module owner → programme lead → stakeholders now |
| S2 High | Gate cannot pass; validation failure without workaround | Module owner → team lead; in the change record |
| S3 Medium | Deviation with workaround; deferrable | Owning team; deviation log; before next gate |
| S4 Low | Cosmetic / documentation | Deviation log; closed in hypercare |

OWNERSHIP PRINCIPLE

One accountable owner per assigned SID, one named guide per owner, controlled change. Multiple engineers must not independently modify the same system.